## Summary
WATFORD AND THREE RIVERS AND DACORUM PCT
Financial Recovery Plan 2006/07
|  |  |  | Opening Saving Dacorum | Opening Saving W3R | Saved to Date | Revised Target | Risk | What this means for practices | Time Scale | Lead
|  |  | Scheme | 2006/07 plan | 2006/07 plan
| working |  |  | £'000 | £'000
risk | ref | 1. TARGET: Reduce Demand in 2nd and Tertiary Care: Director Lead: T. Southam. Clinical Lead(s) : SBJ
m | cas |  | 1:1 Clinical Assessment Service (CAS) (inc Musculoskeletal) | 121.6444 | 169.9662 |  |  | * * | Key specialty areas requiring whole PCT referral management system have been identified and timescaled coming onstream over next 4-8 months. All GP referrals will be sent to one place with exception of ca referrals. Further independent advice indicates even greater savings - PbC ownership and advice welcome. | Project Plan available from 31/03/06. | P. Simms
l | ms |  | 1.2 Minor Surgery Shift (MS, MOS) | 253.0097 | 416.7452 |  |  | * | GP referrals must be made to GP Providers in first instance. Choice Team assisting in appointments. | Commenced on 08/03/06 - ongoing. Eventually will move over to the CAS. | M. Hough
m | pasq |  | 1.3 Practice agreement for set quota of referrals - Practice Based Commissioning | 272.8643 | 426.2354 |  |  | * * | Each Practice will get a quota for elective referrals per specialty and emergency referrals - based upon distance from PCT average. Overall effect is for 10% reduction. | w/c 27/03/06 | J. Phipps
h | c2c |  | 1.4 Consultant to Consultant referrals - secondary care | 51.5359 | 49.1585 |  |  | * * * | Target 5% in Q1+ Q2 followed by 10% Q3 + Q4; practices will be expected to monitor this and give permission as required. Independent advice suggests much greater savings can be aquired - PbC ownership welcomed. |  | T. Southam
m | end |  | 1.5 Gastro Intestinal & Endoscopy referrals 10-15% NICE | 19.1422 | 24.2276 |  |  | * * | Target 10% reduction - over 60% are NAD so practices will be asked to scrutinise their referrals |  | J. Kearney
l |  |  | 1.6 Childrens Service Level Agreement | 60 | 80 |  |  | * | Reduction in SLA being finalised - 5% less activity as with all providers. | 2006-04-17 | C. Pelley
m | dfq |  | 1.7 Follow ups | 942.5011 | 1272.4496 |  |  | * * | Default follow up will be none. GPs will receive clear guidelines on discharge letter that sets out the criteria for ongoing monitoring which is done as part of other routine GP appts. GPs expected to closely monitor quality of discharge letters |  | M. Hough
h | cp |  | 1.8 Chronic Obstructive Pulmonary Disorders | 42.3642 | 53.4856 |  |  | * * * | 20% reduction in admissions through the implementation of the pathway in next three months |  | L. Patten, Corina Chobanou
h | hf |  | 1.9 Heart Failure | 27.1592 | 40.7996 |  |  | * * * | 15% reduction in admissions through implementation of the pathway |  | L. Patten, Russell Jones, Corina Chobanou
h |  |  | 1.10 Diabetes move to Primary Care - Practice based Commissioning |  |  |  |  | * * * | Plan to move diabetologists into PC. Advice and specification from PbC required. | From Q3 | T. Southam
m | derm |  | 1.11 Dermatology move to Primary Care | 31.8935 | 45.5653 |  |  | * * | Pending success of Cas development. Cross Reference Project Plans: 1.1 CAS Development, Discharge. 70% 6 months. | Implement from 1/10 | T. Southam
h |  |  | 1.12 Diagnostics |  |  |  |  | * * * | GP referrals must be made to GP Providers in first instance as in line with the relevant care pathway. Echocardiograms, BNP, 24 hr ECG and ultrasounds. PbC help required to ascertain unmet need & manage demand. |  | T. Southam
2. TARGET: Improved Management of Unscheduled Care: Director Lead: L. Patten. Clinical Lead(s): Dr Essam. (Dac)
h | ucc |  | 2.1 Urgent Care Centre | 1131.0259 | 0 |  |  | * * * | Urgent Care centre possibly at Hemel but only at month 6/7. Before then practices will need to comprehensively look to monitoring their A&E activity and emergency admissions. Currently an options appraisal being looked at across St Albans & Hemel. |  | D. Boardman/ Catch On
h | spoc |  | 2.2 Single Point Of Contact & Rapid Response | 350.4265 | 490.5029 |  |  | * * * | One contact point for GPs and other clinicians to call to activate rapid response team, to avoid hospital admission. |  | G. Snaith
m | ffm |  | 2.3 Frequent Fliers Management | 51.0367 | 71.4377 |  |  | * * | Pre-emptive and pro active management of high risk patients; practices will be expected to monitor this closely and to use the PARR predictive modelling tool to identify potential patients. |  | G. Snaith
#N/A
3. TARGET: Low Priority & Limited Effectiveness Treatment Thresholds: Director Lead: J. Kearney Clinical Lead(s): Richard/Jane Halpin?
l | ceppt |  | 3.1 Paediatric Tonsillectomies/Adenoids | 57.1678 | 68.7034 |  |  | * | Procedure only to be undertaken in exceptional clinical cicumstances. GPs will need to be familiar with referral criteria and with management strategies for pts no longer eligible for treatment. |  | C. Pelley
l | ceppg |  | 3.2 Paediatric Grommets | 23.0677 | 27.8797 |  |  | * | As above |  | C. Pelley
m | cepar |  | 3.3 Athroscopy | 33.8494 | 40.3259 |  |  | * * | As above | Impacts from Q2 | J. Kearney
l | cepbe |  | 3.4 Bat Ears/Circumcision | 8.0236 | 9.957 |  |  | * | Enforcement of existing policy. 10% reduction |  | J. Kearney
l | cepvv |  | 3.5 Varicose Veins | 11.0324 | 12.9441 |  |  | * | Enforcement of existing policy. 10% reduction |  | J. Kearney
4. TARGET: Continuing Care Management: Director Lead: A. Jones. Clinical Lead(s): As Localities
l |  |  | 4.1 Adult Continuing Care | 124.1693 | 149.4951 |  |  | * | Review of all placements and all contractual arrangements. |  | A. Jones
m |  |  | 4.2 Learning Disability Continuing Care | 14 | 16 |  |  | * * | LD handover expected in Q1 |  | A. Jones
h |  |  | 4.3 Section 28a underspend | 104 | 125 |  |  | * * * | Renegotiate S28a across the county (£760k underspend) - should free up some cont care capacity |  | M. Tattersall
5. TARGET: Decommissioning Services: Director Lead: T. Southam. Clinical Lead(s): As Localities
l |  |  | 5.1 Partnership Funding | 31.559 | 46.031 |  |  | * | Notice given to voluntary sector. Savings to be released from Oct 06. List available upon request |  | FC & H. Aylwood
h |  |  | 5.2 Electrically Powered Indoor Outdoor Chairs | 25.6 | 29.215 |  |  | * * * | SHA wide position to be taken as to whether these chairs are financed by the NHS or not. |  | K. Hall
m |  |  | 5.3 London neo-natal disinvestment | 33 | 51 |  |  | * * | Conservative estimate based on 2005/06 actuals |  | C. Pelley
m | htp |  | 5.4 Therapy services - Hydrotherapy | 17.8006 | 22.34 |  |  | * * | Options for future of pool being looked at. May mean provision shifts to local pools. |  | T. Southam
h |  |  | - Soft Tissue Physiotherapy |  |  |  |  | * * * | Effectiveness review of this may have repercussions on the practice based physiotherapy service - and whether it comes under a CAS (see 1.1). Practices will have to refer along same guidelines. | Project Plan available from 31/03/06. | T. Southam
m |  |  | - Other therapies | 67 | 83 |  |  | * * | Effectiveness review of other therapies - some may move to specialist only services. |  | M. Hough
l |  |  | 5.5 Transfer from block to PbR funding | 277 |  |  |  | * | Some services previously in block contract may have to be provided elswhere as PbR may be too expensive. Other areas include increasing anticoag moitoring in Pcare. |  | T. Southam
h |  |  | 5.6 Pain service at WHHT | 10 | 10 |  |  | * * * | Respecification of service - it will be made clear to GPs how referrals are made and who can be referred |  | M. Hough
#N/A
#N/A
#N/A
6. TARGET: CIPS of Directly Managed Services
l |  |  | 6.1 Cost Improvement Plan 5% provider Services | 457 | 445 |  |  | * | Managers currently identifying CIPs through the budget setting process - Practices will be informed if this afects their service | 2006-04-01 | G. Snaith
l |  |  | 6.2 Cost Improvement Plan 5% Management | 214 | 358 |  |  | * | As above | 2006-04-01 | F Cox
l |  |  | 6.3 HV Specification | 0 | 34 |  |  | * | Implementation of minimum spec |  | C.Pelley
m |  |  | 6.4 Reduced costs of PMS practice |  | 71.8362 |  |  | * * | Recommission back to funded level - may mean Practices have to take up some patients previously registered at Meadowell |  | L. Patten
7. TARGET: Reducing MH Inpatient Demand
l |  |  | 7.1 MH Service Level Agreement | 565 | 680 |  |  | * | Public consultation taking place setting out savings proposals. |  | C.Pelley
#N/A
8. TARGET: Better Ways of Working Lead: F. Cox Clinical Lead: R. Walker/N. Brown
l |  |  | 8.1 Prescribing | 855.5 | 1007.6714 |  |  | * | Agreeing budgets for year; agreeing formulary with secondary care; no change to formulary unless through MMGroup with commissioner input to demonstrate cost benefit |  | R. Shah
h |  |  | 8.2 Management costs of clinical networks - Cardiac (TS) - Cancer (FC) - Public Health (JK) |  |  |  |  | * * * | Looking at tighter terms of reference, more effective woking. Networks to own the pathways. |  | F. Cox
h |  |  | 8.3 Better use of PCT estate | 500 | 650 |  |  | * * * | Sale of assets and transfer of receipt from capital to revenue. Lease agreements to link to service provision |  | L. Patten
l |  |  | 8.4 PEC Costs | 74.015 | 87.208 |  |  | * | Reducing beaurocracy but enhancing clinical engagement. |  | F. Cox
9. TARGET: Further areas of work Lead: F. Cox
h |  |  | 9.1 Tertiary referrals |  |  |  |  | * * * | Further analysis required. Requires joint strategy with WHHT |  | T. Southam/ J Kearney
|  |  | Total Identified Savings | 6857.3882 | 7166.1805
|  |  | Required savings | 7600 | 8207
|  |  | Target savings (+33%) | 10108 | 10915.31
h |  |  | Summary of High Risk | 2242.1116 | 1448.1616 |  |  | * * *
m |  |  | Summary of Medium Risk | 1604.7322 | 2294.3839 |  |  | * *
l |  |  | Summary of Low Risk | 3010.5444 | 3423.635 |  |  | *
|  |  | Total | 6857.3882 | 7166.1805
|  |  | Check error | 0 | 0
0
l | *
m | * *
h | * * *
| ucc |  |  | 1131.0259 | 0
| ms |  |  | 253.0097 | 416.7452
| end |  |  | 19.1422 | 24.2276
| c2c |  |  | 51.5359 | 49.1585
| hf |  |  | 27.1592 | 40.7996
| cp |  |  | 42.3642 | 53.4856
| cas |  |  | 121.6444 | 169.9662
| derm |  |  | 31.8935 | 45.5653
| spoc |  |  | 350.4265 | 490.5029
| ffm |  |  | 51.0367 | 71.4377
| pasq |  |  | 272.8643 | 426.2354
| dfq |  |  | 942.5011 | 1272.4496
| ceppt |  |  | 57.1678 | 68.7034
| ceppg |  |  | 23.0677 | 27.8797
| cepar |  |  | 33.8494 | 40.3259
| cepbe |  |  | 8.0236 | 9.957
| cepvv |  |  | 11.0324 | 12.9441
| htp |  |  | 17.8006 | 22.34
| chk |  |  | 0 | 0

## Workings
FRG | Project | W3R savings | [5 empty] | Dac savings | [5 empty] | Both PCTs | Scheme | Scheme | Part Year | Benefit | Benefit
group | ref | EL | N El | 1st OP | FU OP | A&E | Tot | EL | N El | 1st OP | FU OP | A&E | Tot | savings | Costs | Benefit | Effect | W3R | Dac
| UCC | [5 empty] | 0 |  | 1363409.4571 |  |  | 825616.4 | 2189025.8571 | 2189025.8571 | 1050000 | 1139025.8571
| FFM costs | [5 empty] | 0 | [5 empty] | 0 | 0 | 8000 | -8000
ucc | UCC net | [5 empty] | 0 |  | 1363409.4571 |  |  | 825616.4 | 2189025.8571 | 2189025.8571 | 1058000 | 1131025.8571 |  |  | 1131025.8571
[7 empty] | 0 | [5 empty] | 0 | 0 |  | 0
ms | MOS | 97118.5418 |  | 14833.7778 | 7562.9258 |  | 119515.2454 | 70809.1278 |  | 10625.641 | 5433.313 |  | 86868.0819 | 206383.3273 | 39978.6667 | 166404.6607 |  | 96363.859 | 70040.8016
c2c | C2C |  |  | 49158.5306 |  |  | 49158.5306 |  |  | 51535.9088 |  |  | 51535.9088 | 100694.4394 |  | 100694.4394 |  | 49158.5306 | 51535.9088
ms | MS | 453377.6058 |  |  |  |  | 453377.6058 | 258922.6745 |  |  |  |  | 258922.6745 | 712300.2803 | 208950 | 503350.2803 |  | 320381.3775 | 182968.9028
end | end | 24227.6312 |  |  |  |  | 24227.6312 | 19142.171 |  |  |  |  | 19142.171 | 43369.8021 |  | 43369.8021 |  | 24227.6312 | 19142.171
hf | HFNS-HFRS |  | 54399.4 |  |  |  | 54399.4 |  | 36212.2 |  |  |  | 36212.2 | 90611.6 | 22652.9 | 67958.7 | 100% | 40799.55 | 27159.15
cp | CPRS-CPC |  | 71314.1333 |  |  |  | 71314.1333 |  | 56485.6533 |  |  |  | 56485.6533 | 127799.7867 | 31949.9467 | 95849.84 | 100% | 53485.6 | 42364.24
cas | MSKT |  |  | 214131.0882 |  |  | 214131.0882 |  |  | 154245.4043 |  |  | 154245.4043 | 368376.4925 | 142458.3944 | 225918.098 |  | 131322.4084 | 94595.6897
[7 empty] | 0 | [5 empty] | 0 | 0 |  | 0
derm | DERM |  |  | 120225.0638 |  |  | 120225.0638 |  |  | 84151.62 |  |  | 84151.62 | 204376.6838 | 126917.9206 | 77458.7632 |  | 45565.2992 | 31893.464
[7 empty] | 0 | [5 empty] | 0 | 0
spoc | SPOC |  | 577995.9544 |  |  |  | 577995.9544 |  | 412933.4428 |  |  |  | 412933.4428 | 990929.3972 | 150000 | 840929.3972 |  | 490502.9469 | 350426.4502
[7 empty] | 0 | [5 empty] | 0 | 0
ffm | FFM |  | 71437.7022 |  |  |  | 71437.7022 |  | 51036.7176 |  |  |  | 51036.7176 | 122474.4199 |  | 122474.4199 |  | 71437.7022 | 51036.7176
[7 empty] | 0 | [5 empty] | 0 | 0 |  | 0
pasq | PASQ |  |  | 426235.377 |  |  | 426235.377 |  |  | 272864.3495 |  |  | 272864.3495 | 699099.7265 |  | 699099.7265 |  | 426235.377 | 272864.3495
dfq | DFQ |  |  |  | 1272449.604 |  | 1272449.604 |  |  |  | 942501.091 |  | 942501.091 | 2214950.695 |  | 2214950.695 |  | 1272449.604 | 942501.091
cep | CEP | 138601.7265 |  |  |  |  | 138601.7265 | 115539.1252 |  |  |  |  | 115539.1252 | 254140.8516 |  | 254140.8516 |  | 138601.7265 | 115539.1252
cas | CAS |  |  | 51525.0273 |  |  | 51525.0273 |  |  | 36064.98 |  |  | 36064.98 | 87590.0073 | 21897.5018 | 65692.5055 |  | 38643.7705 | 27048.735
[7 empty] | 0 | [5 empty] | 0 | 0 |  | 0 |  | 0 | 0
| Tot | 713325.5053 | 775147.19 | 876108.8647 | 1280012.5298 | 0 | 3644594.0897 | 464413.0984 | 1920077.4708 | 609487.9036 | 947934.404 | 825616.4 | 4767529.2769 | 8412123.3666 | 1802805.3302 | 6609318.0364 |  | 3199175.3828 | 3410142.6536
| chk | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  | 0
0
non-SLA projects/extra-SLA calculations:
|  | hydro-therapy pool FOT 2005/6 | [11 empty] | 89800
|  | Part year 9/12 | [11 empty] | 67350
|  | PCT shares of total | [15 empty] | 33.17% | 26.43%
htp | htp | Net benefit | [14 empty] | PYE | 22339.995 | 17800.605
ceppt | mt analysis: | 69 |  |  |  |  | mt analysis: | 57 |  |  |  |  | child price uplift: | 1.25 |  |  | 100% | 68703.442 | 57167.7963
ceppg | mt analysis: | 28 |  |  |  |  | mt analysis: | 23 |  |  |  |  | child price uplift: | 1.25 |  |  | 100% | 27879.6576 | 23067.7073
cepar | mt analysis: | 54 |  |  |  |  | mt analysis: | 45 |  |  |  |  | child price uplift: | 1.25 |  |  | 75% | 40325.9333 | 33849.3531
cepbe | mt analysis: | 10 |  |  |  |  | mt analysis: | 8 |  |  |  |  | child price uplift: | 1.25 |  |  | 100% | 9957.0206 | 8023.5504
cepvv | mt analysis: | 13 |  |  |  |  | mt analysis: | 11 |  |  |  |  | child price uplift: | 1.25 |  |  | 100% | 12944.1268 | 11032.3817
[18 empty] | -13441.9778 | -11283.1177
chk | per summary | [16 empty] | 3242723.8317 | 3445544.9222